## Week 1
Date | Person | Duration | Description
2022-02-07 | Lenny | 6 hours | Beginning of project: initial research, finding tools, setting up documents
2022-02-07 | Arno | 4 hours | Beginning of project: searching for tools looking up subject
2022-02-07 | Zehra | 6 hours | Beginning of project: initial research, finding tools, setting up documents
2022-02-07 | Dries | 6 hours | Beginning of project: initial research, finding tools, setting up documents
2022-02-08 | Lenny | 2 hours | Deploying and trying out Rudder
2022-02-08 | Arno | 2 hours | Doing initial research of juju & installing juju
2022-02-09 | Lenny | 4 hours | Setting up GitLab (milestones etc), setting up timesheet, work on paper
2022-02-09 | Arno | 4 hours | Continuing juju research, researching stackstorm, working on paper
2022-02-09 | Zehra | 4 hours | Looking for newest tools, research + working on paper
2022-02-09 | Dries | 4 hours | Tool research, writing paper
2022-02-10 | Dries | 1,5 hours | Rewriting paper (Dutch->English), writing Ansible part
2022-02-11 | Lenny | 4 hours | Detailing Chef Infra in the paper, general work on paper (proofreading, correcting, ...) and setting up planning in GitLab
2022-02-11 | Dries | 6 hours | Working on ansible playbook that deploys a simple app.
2022-02-11 | Zehra | 4 hours | Researching Puppet + writing paper
2022-02-11 | Arno | 4 hours | Writing terraform theory in paper, researching terraform ( reading docs ... )
2022-02-12 | Dries | 1 hour | Finished ansible playbook for a simple deployment of the .NET app. Might need to fix an issue with the connection being refused.

## Week 2
Date | Person | Duration | Description
2022-02-14 | Arno | 6 hours | Setting up Terraform POC + working on paper
2022-02-14 | Zehra | 6 hours | Puppet documentation + paper, figuring out how to deploy
2022-02-14 | Dries | 6 hours | Finished agentless vs agent-based architecture. Finished How does it work (ansible) and removed unnecessary plays in ansible playbook.
2022-02-14 | Lenny | 6 hours | Finishing Chef Infra theory part, investigating Chef Infra deployment, working on StackStorm theoretical part and writing out mutable vs immutable infrastructure in the paper
2022-02-16 | Lenny | 3,5 hours | Working on StackStorm theory + figuring out JIRA integrations with StackStorm
2022-02-16 | Arno | 3,5 hours | Finishing terraform poc and writing in paper
2022-02-16 | Zehra | 3,5 hours | Gathering information Configuration management vs Provisioning tools, Fixing Puppet installation
2022-02-16 | Dries | 4 hours | Rewritten types of architecture. Terraform tool. Working on Ansible vs. Terraform (Ansible cloud deployment part)
2022-02-18 | Lenny | 4 hours | Working on StackStorm + reviewing issues
2022-02-18 | Dries | 4 hours | Rewriting paper where necessary, working on ansible vs terraform
2022-02-18 | Arno | 4 hours | writing provisioning vs configuration managemet in paper, reviewing parts of the paper & start researching stackstorm deployment using terraform
2022-02-18 | Zehra | 4 hours | Following Puppet tutorial
2022-02-20 | Lenny | 0,5 hours | Preparing sprint review
2022-02-20 | Zehra | 0,5 hours | Preparing sprint review
2022-02-20 | Dries | 0,5 hours | Preparing sprint review
2022-02-20 | Arno | 0,5 hours | Preparing sprint review
2022-02-20 | Dries | 2,5 hours | Working on Ansible vs Terraform (Asnible playbooks: finished deployment and destruction of cloud instances)

## Week 3
Date | Person | Duration | Description
2022-02-21 | Lenny | 6 hours | Setting up AD server + sprint review + setting up proper issues in GitLab + StackStorm POC brainstorming + trying out JIRA integration
2022-02-21 | Arno | 6 hours | Working on stackstorm deployment onto vm with Terraform and Ansible + brainstorming about Stackstorm POC + trying out Nagios integration
2022-02-21 | Dries | 6 hours | Almost done with Ansible vs Terraform: ansible playbooks, had some issues but fixed most of them. Need to finish testing later, waiting on propagation of ssh metadata.
2022-02-21 | Zehra | 5 hours | Reading more about StackStorm + brainstorming StackStorm POC + sprint review
2022-02-22 | Arno | 2,5 hours | Finishing Stackstorm deployment with Terraform & going through stackstorm quick start
2022-02-22 | Dries | 3 hours | Finished stackstorm quick start guide. Finished Ansible vs Terraform ansible playbooks, started writing this part in the paper, will finish it tomorrow.
2022-02-22 | Zehra | 1 hours | StackStorm quick start
2022-02-23 | Dries | 3 hours | Finished Ansible vs Terraform, added extra info in the event-driven part of the paper, removed redundant part. Working on Stackstorm integration with Active Directory.
2022-02-23 | Lenny | 3 hours | Finishing Stackstorm QS + setting up JIRA Integration + creating some more GitLab issues
2022-02-23 | Arno | 4 hours | Finished Ansible vs Terraform , deployed local nagios instance and seeing how nagios integration with stackstorm works
2022-02-23 | Zehra | 3 hours | Looking into Mailgun and sending mails with event + Reading documentation of Actions and configs +
2022-02-24 | Arno | 1 hour | Finished nagios integration into stackstorm
2022-02-25 | Lenny | 4 hours | Working on POC 1
2022-02-25 | Zehra | 4 hours | Trying to figure out gitlab integration
2022-02-25 | Dries | 3,5 hours | AD setup and StackStorm integration
2022-02-27 | Dries | 1 hour | POC brainstorm
2022-02-27 | Zehra | 1 hour | POC brainstorm
2022-02-27 | Lenny | 1 hour | POC brainstorm
2022-02-27 | Arno | 1 hour | POC brainstorm
2022-02-27 | Dries | 4,5 hours | Puppet: deploy .net app: added installation of puppetserver, puppetclient
2022-02-28 | Arno | 1 hour | Setting up twitter developer portal + researching titter stackstorm integration
2022-02-28 | Lenny | 1 hour | Checking out workflow engine
2022-02-28 | Dries | 4 hours | Puppet: deploy .net app: fixed certificates
2022-03-01 | Arno | 1,5 hours | Making my own custom nagios docker image because the ones on dockerhub where outdated or incomplete
2022-03-01 | Dries | 5,5 hours | Puppet: deploy .net app: working on manifest file that deploys the .NET app
2022-03-01 | Dries | 2 hours | Puppet: deploy .net app: fixing manifest errors
2022-03-02 | Dries | 1 hour | Puppet: deploy .net app: fixing manifest errors
2022-03-03 | Dries | 2 hours | Puppet: deploy .net app: docker image gets build, problem with running the image
2022-03-04 | Arno | 2,5 hours | having some problems with the apache and nagios service not starting on booting the image & sucsesfully checking services with nagios, Researching the way to add hosts and services to monitor
2022-03-06 | Zehra | 2 hours | POC brainstorm

## Week 4
Date | Person | Duration | Description
2022-03-07 | Dries | 3 hours | Puppet: deploy .net app: solved all errors with the manifest file
2022-03-07 | Dries | 2,5 hours | started working on 'Chef: deploy .net app' issue
2022-03-07 | Lenny | 6 hours | Working on POC 1 + created a tiny custom pack to generate a password
2022-03-07 | Arno | 5,5 hours | Working on nagios & Twitter POC - sucesfully activated Trigger when host goes down & applied for Twitter elevated access, tried using nagiosql but found out its outdated
2022-03-07 | Zehra | 6 hours | Learning how to make packs, runners, examining already existing packs, writing basic addition pack
2022-03-08 | Arno | 0,5 hours | POC2 : Created a rule that sends a tweet when a server goes down
2022-03-09 | Lenny | 3 hours | Finishing POC 1
2022-03-09 | Arno | 3,5 hours | Finishing POC 2
2022-03-09 | Zehra | 3,5 hours | Learning Python + reading doc
2022-03-11 | Lenny | 3 hours | Writing documentation on POC 1 + cleaning up into one pack
2022-03-11 | Arno | 3 hours | Documenting POC 2
2022-03-11 | Dries | 1 hour | Chef: deploy .net app: working on Chef Infra server & client installation
2022-03-11 | Zehra | 3 hours | looking at existing sensors and trying to write sensor
2022-03-12 | Dries | 2,5 hours | Chef: deploy .net app: finished Chef Infra server installation
2022-03-13 | Zehra | 2 hours | Working on POC 4

## Week 5
Date | Person | Duration | Description
2022-03-14 | Zehra | 6 hours | Working on POC 4, python module is not working on stackstorm?
2022-03-14 | Lenny | 5 hours | POC 1 Documentation + trying some new things
2022-03-14 | Arno | 0,5 hours | Testing working of POC
2022-03-14 | Zehra | 5 hours | POC 4: Trying to debug python-apt in requirements.txt + Writing sensor for hard disk
2022-03-14 | Dries | 5 hours | Chef: deploy .NET app, fixing issues
2022-03-16 | Lenny | 45 minutes | Finalising POC 1 documentation
2022-03-17 | Lenny | 3 hours | Finishing POC 3
2022-03-17 | Arno | 1 hours | Adding some extra documentation to POC2
2022-03-17 | Dries | 3 hours | Chef: deploy .NET app, fixing issues
2022-03-17 | Zehra | 3 hours | LVM leren + proberen op cloud
2022-03-18 | Dries | 4 hours | Chef: deploy .NET app, switching to Vagrant (local chef provisioner to work arround issues.
2022-03-18 | Arno | 3 hours | POC2 changing rule to workflow + integration mailgun into poc
2022-03-20 | Arno | 1 hour | POC 2 rewirting part of documentation
2022-03-20 | Dries | 1,5 hours | POC 2 rewirting part of documentation
2022-03-20 | Zehra | 4 hours | Finishing POC 4

## Week 6
Date | Person | Duration | Description
2022-03-21 | Arno | 4,5 hours | discussing presentation , writing text , helping Dries with some text in Paper
2022-03-21 | Dries | 4,5 hours | discussing presentation, writing text, finished comparison of usual suspects
2022-03-21 | Lenny | 4,5 hours | discussing presentation, writing text, finished comparison of usual suspects
2022-03-22 | Dries | 0,5 hours | working text
2022-03-22 | Arno | 1 hour | working on presentation & recording demo video
2022-03-23 | Arno | 3 hour | Working on presentation
2022-03-23 | Lenny | 3 hours | Working on presentation
2022-03-23 | Zehra | 1 hour | Working on presentation
2022-03-24 | Lenny | 1 hour | Basic presentation dry-run & timing
2022-03-24 | Zehra | 45 minutes | Basic presentation dry-run & timing
2022-03-24 | Dries | 1 hour | Basic presentation dry-run & timing
2022-03-24 | Arno | 1 hour | Basic presentation dry-run & timing
2022-03-24 | Zehra | 4 hour | Writing more text for presentation + figuring out config file for POC
2022-03-25 | Arno | 2 hours | doing dry run & finalizing text
2022-03-25 | Zehra | 1 hour | Working on article
2022-03-25 | Lenny | 2 hours | Dry run + article + proof reading paper
2022-03-25 | Dries | 2 hours | Proof reading paper, dry run
2022-03-26 | Zehra | 6 hours | Making config file work
2022-03-26 | Lenny | 2 hours | Working on demo's, preparing for presentation + working on presentation
2022-03-28 | Zehra | 3,5 hours | Documenting POC 4

## Backend (hidden)
Lenny
Zehra
Dries
Arno